## Sheet1
BUG LOG REPORT
Team Name - Person's Name
Bug Number | Severity Level | Date Created | Section | Description | Identified by | How to replicate | Status | Root Cause | Resolution | Fixed On | Assigned To | Fixed By
1 | Medium | 2015-10-16 | Gameplay | Controllers continue to vibrate after player death. | Jc | Get hit at the point of death. | To Be Tested | Vibration only turns of On Orbs that are Alive | Move the stop vibrate functions out of the alive check |  | Jc
2 | High | 2015-10-16 | Gameplay | Tunneling. | Jc + Austin | Boost next to a player in their direction. | To Be Tested | Time step Of processing was too large | Issue is no longer Present, Process was moved out of the frame/time check | 2015-10-16 | Jc | Jc
3 | Critical | 2015-10-16 | Gameplay | Having less controllers than the selected players disrupts all gameplay until controllers are connected | Jc | Select more players than you have controllers for | To Be Tested | No check on number of contolers before selcting number of players | Adding in the Check only allowing transision to game if the correct number of controllers are present | 27//10/2015 | Jc | Juran
4 | Medium | 2015-10-16 | Menu | Pause Menus Options do not change the options | Juran | Open the Options Menu from the Pause Menu and try to change options. | To Be Tested | Was not implimented | Research indicated that options in pause menus where rarely used therefor options menu was removed from the Pause menu | 27//10/2015 | Juran | Juran
5 | Medium | 2015-10-27 | Lobby | Players do not know which char they are at game start. | Phenomena |  |  | Connection between controllers and Characters where not obvious to the players | Add a lobby screen that depicts the color and location of player. |  | Juran
6 | Low | 2015-10-27 | Gameplay | Players get punished by mistakes to quickly, no learning curve. | Juran + Austin |  | To Be Tested (Needs Visuals) | No time for a player to learn and make mistakes | Adding Matches with multiple rounds (First to 3). Allowing players to make mistakes with out punishing the player too much |  | Jc | Jc
7 | Low | 2015-10-27 | Options | No Feed back of rumble change | Phenomena |  |  |  | Vibrate the Controller when Turning the Rumble On |  | Juran
8 | Medium | 2015-10-27 | Sound | Sound stop playing | Callan + Jc | 30th Sound Played - kills background sound |  |  |  |  | Juran
9 | Medium | 2015-10-27 | Instructions | Returning from Intructions is mapped to the incorrect Button | Callan + Jc | Game is with in the Instructions Screen | To Be Tested | Incorrect Buttom checking | Remap keys on Instrcutions Screen | 27//10/2015 | Juran | Juran
10 | Medium | 2015-10-27 | Pause | Pause menu items are not clearly visible | Callan + Jc | Pause the Game |  |  | Change color of Pause menu text to White Inner |  | Juran
11 | Low | 2015-10-27 | Match Start | Match Start Timer placement | Callan + Jc | Start the Match |  |  | Move playement of The Start timer to the centre, enlarge, and change the text color to white |  | Juran
12 | Medium | 2015-10-27 | Missing Controllers | No Pause/Contol when missing controllers | Callan + Jc | Remove a connected contoller |  |  | Allow Control (With in the pause menu) by other Contollers/players when one of the contollers is missing |  | Jc + Juran
13 | Medium | 2015-10-27 | Timer | Match Timer and Tiles are not synced | Callan + Jc | Run Down the match timer |  |  |  |  | Callan
14 | Medium | 2015-10-27 | Sound | No Victory Music | Callan + Jc | Win a Match |  |  |  |  | Juran
15 | Medium | 2015-10-27 | UI | "Press A to Continue" Text missing from victory Screen | Callan + Jc | Win a Match |  |  |  |  | Juran
16 | Medium | 2015-10-27 | UI | "Connect A Xbox Contoller" Text missing from menus | Callan + Jc | Be in any menu with no contoller Connected |  |  |  |  | Juran
17 | Medium | 2015-10-27 | Sound | Ability Sound Effect do not play | Callan + Jc | Activate the Boost/Phase abilities |  |  |  |  | Juran
18 | High | 2015-10-27 | Gameplay | Collisions are incorrect in Release | Callan + Jc | Run game in Release |  |  |  |  | Callan + Jc
19 | High | 2015-10-27 | Gameplay | Friction is almost instant with in Release | Callan + Jc | Run game in Release |  |  |  |  | Callan + Jc
20 | High | 2015-10-27 | Gameplay | Movements acts incorectly With in Release compared to Debug | Callan + Jc | Run game in Release |  |  |  |  | Callan + Jc
22 | Critical | 2015-10-27 | Build | Release runs differently comapared to debug, mainly connected to movement and collisions | Callan + Jc | Run game in debug and release Build |  |  |  |  | Callan
23 | Low | 2015-10-27 | Graphic | Graphical glitch on orbs when moving to fast | Callan + Jc | Move Orb Fast | To Be Tested | The Glow light does not reflect the exact position of the Orb (It is slightly behind) | Kept Due to the fact it gives players a a sense of a direction they are moving in. | 27//10/2015 | Callan | Callan
24 | Medium | 2015-10-27 | Menu | When player One Controller not plugged in game tell me to connect controller but player 2 contoller is plugged in | Phenomena | 2 controllers plugged in at the start, remove player ones controller |  | Only Player one is listened to in menus |  |  | Juran
25 | Critical | 2015-10-27 | Menu | Game Crashes when coming out of a menu item from the pause menu | Phenomena | Pause the Game - the press B |  |  |  |  | Juran

## Test 01
Test Number | Test ID | Scenario | Tested By | Date | Outcome | Details (If Failed)
1.01 | TC_MENU_00 | Run Game | Callan + Jc | 2015-10-27 | Passed
1.02 | TC_MENU_01 | Menu Screen - no Controller Test | Callan + Jc | 2015-10-27 | Failed | The "Connect Xbox controler" does not show
1.03 | TC_MENU_02 | Menu Screen - Transition Test | Callan + Jc | 2015-10-27 | Passed
1.04 | TC_MENU_03 | Match Set Up Screen- no Controller Test | Callan + Jc | 2015-10-27 | Failed | The "Connect Xbox controler" does not show
1.05 | TC_MENU_04 | Match Set Up Screen - Transition Test | Callan + Jc | 2015-10-27 | Passed
1.06 | TC_MENU_05 | Options Screen - no Controller Test | Callan + Jc | 2015-10-27 | Failed | The "Connect Xbox controler" does not show
1.07 | TC_MENU_06 | Options Screen - Transition Test | Callan + Jc | 2015-10-27 | Passed | Recommendation on Feedback when turning Rumble On
1.08 | TC_MENU_07 | Instructions Screen - no Controller Test | Callan + Jc | 2015-10-27 | Failed | The "Connect Xbox controler" does not show
1.09 | TC_MENU_08 | Instructions Screen - Transition Test | Callan + Jc | 2015-10-27 | Failed | "B" does not return ("A" returns)
1.1 | TC_MENU_09 | Pause Screen - no Controller Test | Callan + Jc | 2015-10-27 | Failed | The "Connect Xbox controler" does not show
1.11 | TC_MENU_10 | Pause Screen - Transition Test | Callan + Jc | 2015-10-27 | Failed | Menu Items Are not "clearly" visible. Typo - Text says "Exit" instead of "Quit"
1.12 | TC_GAME_00 | Match Start | Callan + Jc | 2015-10-27 | Passed
1.13 | TC_GAME_01 | Controller Test | Callan + Jc | 2015-10-27 | Passed
1.14 | TC_GAME_02 | Match Timer | Callan + Jc | 2015-10-27 | Failed | Time reaches 0 before tiles are gone
1.15 | TC_GAME_03 | Winning a Match | Callan + Jc | 2015-10-27 | Failed | No Victory Music
1.16 | TC_GAME_04 | Match End | Callan + Jc | 2015-10-27 | Failed | "Press A to Continue" Not visible
1.17 | TC_GAME_TILE_01 | Tiles - Fadeing | Callan + Jc | 2015-10-27 | Passed
1.18 | TC_GAME_TILE_02 | Tiles - Slippery | Callan + Jc | 2015-10-27 | Passed
1.19 | TC_GAME_TILE_03 | Tiles - Sticky | Callan + Jc | 2015-10-27 | Passed
1.2 | TC_GAME_TILE_04 | Tiles - Friction | Callan + Jc | 2015-10-27 | Failed | Deceleration is almost intant
1.21 | TC_GAME_ORB_01 | Player Movement | Callan + Jc | 2015-10-27 | Passed
1.22 | TC_GAME_ORB_02 | Ability Boost | Callan + Jc | 2015-10-27 | Failed | No Sound Effect
1.23 | TC_GAME_ORB_03 | Ability Phase | Callan + Jc | 2015-10-27 | Failed | No Sound Effect
1.24 | TC_GAME_ORB_04 | Character Death | Callan + Jc | 2015-10-27 | Passed
1.25 | TC_GAME_ORB_05 | Collisions | Callan + Jc | 2015-10-27 | Failed | Incorrect Expected Result

## Test 02
Test Number | Test ID | Scenario | Tested By | Date | Outcome | Details (If Failed)
2.01 | TC_MENU_00 | Run Game | Phenomena | 2015-10-27 | Passed
2.02 | TC_MENU_01 | Menu Screen - no Controller Test | Phenomena | 2015-10-27 | Failed | Player 2 controller was still plugged in, but "connect controler" text was pressent
2.03 | TC_MENU_02 | Menu Screen - Transition Test | Phenomena | 2015-10-27 | Passed
2.04 | TC_MENU_03 | Match Set Up Screen- no Controller Test | Phenomena | 2015-10-27 | Passed | To be Updated
2.05 | TC_MENU_04 | Match Set Up Screen - Transition Test | Phenomena | 2015-10-27 | Passed | To be Updated
2.06 | TC_MENU_05 | Options Screen - no Controller Test | Phenomena | 2015-10-27 | Failed | Player 2 controller was still plugged in, but "connect controler" text was pressent
2.07 | TC_MENU_06 | Options Screen - Transition Test | Phenomena | 2015-10-27 | Passed
2.08 | TC_MENU_07 | Instructions Screen - no Controller Test | Phenomena | 2015-10-27 | Failed | Player 2 controller was still plugged in, but "connect controler" text was pressent
2.09 | TC_MENU_08 | Instructions Screen - Transition Test | Phenomena | 2015-10-27 | Passed
2.1 | TC_MENU_09 | Pause Screen - no Controller Test | Phenomena | 2015-10-27 | Passed
2.11 | TC_MENU_10 | Pause Screen - Transition Test | Phenomena | 2015-10-27 | Failed | Press "B" Crashes the Game
2.12 | TC_MENU_11 | Sound Test | Phenomena | 2015-10-27 | Failed | Bug Still Pressent
2.13 | TC_GAME_00 | Match Start | Phenomena | 2015-10-27 | Passed
2.14 | TC_GAME_01 | Controller Test | Phenomena | 2015-10-27 | Passed
2.15 | TC_GAME_02 | Match Timer | Phenomena | 2015-10-27 | Passed
2.16 | TC_GAME_03 | Winning a Match | Phenomena | 2015-10-27 | Failed | Game Crashs
2.17 | TC_GAME_04 | Match End | Phenomena | 2015-10-27 | To be Tested | Acceptance Test plan requires Update
2.18 | TC_GAME_05 | Sound Test | Phenomena | 2015-10-27 | Failed | Bug Still Pressent
2.19 | TC_GAME_TILE_01 | Tiles - Fadeing | Phenomena | 2015-10-27 | Passed
2.2 | TC_GAME_TILE_02 | Tiles - Slippery | Phenomena | 2015-10-27 | Passed
2.21 | TC_GAME_TILE_03 | Tiles - Sticky | Phenomena | 2015-10-27 | Failed | No Effect (TO BE LOGGED)
2.22 | TC_GAME_TILE_04 | Tiles - Friction | Phenomena | 2015-10-27 | Passed
2.23 | TC_GAME_ORB_01 | Player Movement | Phenomena | 2015-10-27 | Passed
2.24 | TC_GAME_ORB_02 | Ability Boost | Phenomena | 2015-10-27 | Failed | No sound Effect, Not Enough "boost" (TO BE LOGGED)
2.25 | TC_GAME_ORB_03 | Ability Phase | Phenomena | 2015-10-27 | Failed | No Sound Effect
2.26 | TC_GAME_ORB_04 | Character Death | Phenomena | 2015-10-27 | To be Tested | Acceptance Test plan requires Update
2.27 | TC_GAME_ORB_05 | Collisions | Phenomena | 2015-10-27 | Failed | Very small velocity can result in irregularities (TO BE LOGGED)